|  |  |
| --- | --- |
| ***Task*** | ***Due Date*** |
| Wave 1: Survey recruitment at local level-confirm participation with DAODAS | June 30, 2023 |
| DAODAS provides County Alcohol and Drug prevention staff the new draft survey to review with school officials. Feedback to DAODAS by August 3 | June 16- August 3, 2023 |
| Wave 2: Survey recruitment at local level-confirm participation with DAODAS | October 31, 2023 |
| Additional questions to be added to school-specific surveys | November 17, 2023 |
| Initial Survey administration instructional training | December 4-8, 2023 |
| Final/follow-up survey administration instructional training | January 8-12, 2024 |
| All survey administration instructions e-mailed to named contact in each county. | January 12, 2024 |
| Survey administered to students. | January 22-March 15, 2024 |
| Quality Control and analytic period | April-May 2024 |
| Highlights from State report provided at May Prevention Quarterly Meeting | May 2, 2024 |
| Data Reports sent to County Authority Contacts. | Before June 30, 2024 |

